## Sheet1
Task | Start Date | End Date | Duration
SGTours | 2022-04-09 | 2022-08-27 | 140
1
PROJECT PLANNING |  |  | 1
Scheduling | 2022-04-10 | 2022-04-12 | 3
Resource Planning | 2022-04-10 | 2022-04-12 | 3
Project Website | 2022-04-13 | 2022-04-13 | 1
RESEARCH ON PROJECT TOPIC | 2022-04-13 | 2022-04-16 | 4
Identifying functional requirements |  |  | 1
Develop Use Cases |  |  | 1
PROJECT REQUIREMENT | 2022-04-16 | 2022-04-30 | 15
Finalizing functional requirements | 2022-04-16 | 2022-04-18 | 3
Non-functional features | 2022-04-18 | 2022-04-19 | 2
Security Features | 2022-04-19 | 2022-04-20 | 2
Develop Use Case Diagram | 2022-04-16 | 2022-04-20 | 5
Develop Use Case Description | 2022-04-16 | 2022-04-20 | 5
SYSTEM REQUIREMENT | 2022-04-30 | 2022-05-18 | 19
Identifying functional requirements |  |  | 1
Identify Algorithms |  |  | 1
Interfaces Required |  |  | 1
1
Sprint 3 | 2022-04-28 | 2022-05-09 | 12
Develop Use Case Diagram | 2022-04-28 | 2022-05-05 | 8
Develop Use Case Description | 2022-04-28 | 2022-05-05 | 8
Develop Sequence Diagram | 2022-04-28 | 2022-05-05 | 8
Develop BCE Class Diagram | 2022-04-28 | 2022-05-05 | 8
Develop BCE Sequence Diagram | 2022-04-28 | 2022-05-05 | 8
Wireframing | 2022-05-04 | 2022-05-05 | 2
Develop front end | 2022-04-28 | 2022-05-08 | 11
Develop back end | 2022-04-28 | 2022-05-08 | 11
Testing | 2022-05-09 | 2022-05-09 | 1
End of Sprint 3 | 2022-05-09 | 2022-05-09 | 1
Sprint 4 | 2022-05-10 | 2022-05-19 | 10
Develop Use Case Diagram | 2022-05-10 | 2022-05-13 | 4
Develop Use Case Description | 2022-05-10 | 2022-05-13 | 4
Develop Sequence Diagram | 2022-05-10 | 2022-05-13 | 4
Develop BCE Class Diagram | 2022-05-10 | 2022-05-13 | 4
Develop BCE Sequence Diagram | 2022-05-10 | 2022-05-13 | 4
Wireframing | 2022-05-13 | 2022-05-13 | 1
Develop front end | 2022-05-14 | 2022-05-18 | 5
Develop back end | 2022-05-14 | 2022-05-18 | 5
Testing | 2022-05-19 | 2022-05-19 | 1
End of Sprint 4 | 2022-05-19 | 2022-05-19 | 1
Sprint 5 | 2022-05-20 | 2022-05-28 | 9
Develop Use Case Diagram | 2022-05-20 | 2022-05-23 | 4
Develop Use Case Description | 2022-05-20 | 2022-05-23 | 4
Develop Sequence Diagram | 2022-05-20 | 2022-05-23 | 4
Develop BCE Class Diagram | 2022-05-20 | 2022-05-23 | 4
Develop BCE Sequence Diagram | 2022-05-20 | 2022-05-23 | 4
Wireframing | 2022-05-24 | 2022-05-24 | 1
Develop front end | 2022-05-24 | 2022-05-28 | 5
Develop back end | 2022-05-24 | 2022-05-28 | 5
Final Testing | 2022-05-28 | 2022-05-28 | 1
End of Sprint 5 | 2022-05-28 | 2022-05-28 | 1
Final Submission | 2022-05-28 | 2022-05-28 | 1

## ProjectSchedule
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | SGTours |  |  |  |  | SIMPLE GANTT CHART by Vertex42.com
Enter Company Name in cell B2. | FYP-22-S2-29P |  |  |  |  | https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Project Start: label is in cell C3. |  | Project Start: | 2022-04-09
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display Week: | 1 |  |  | 2022-04-07 | [6 empty] | 2022-04-11 | [6 empty] | 2022-04-18 | [6 empty] | 2022-04-25 | [6 empty] | 2022-05-02 | [6 empty] | 2022-05-09 | [6 empty] | 2022-05-16 | [6 empty] | 2022-05-23
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2022-04-04 to 2022-05-29
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | ASSIGNED TO | START | END | DAYS | time axis 2022-04-04 to 2022-05-29
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | PROJECT PLANNING
| Scheduling |  | 2022-04-10 | 2022-04-12
| Resource Planning |  | 2022-04-10 | 2022-04-12
| Project Website |  | 2022-04-13 | 2022-04-13
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | RESEARCH ON PROJECT TOPIC
| Gather requirements from stakeholders |  | 2022-04-13 | 2022-04-16
| Research on existing applications |  | 2022-04-13 | 2022-04-17
| Identifying functions from existing applications |  | 2022-04-13 | 2022-04-17
| Software Development Methodologies |  | 2022-04-14 | 2022-04-17
| Develop Use Cases |  | 2022-04-18 | 2022-04-29
Sample phase title block | PROJECT REQUIREMENT
| Finalizing functional requirements |  | 2022-04-29 | 2022-05-17
| Non-functional features |  | 2022-04-29 | 2022-05-17
| Security Features |  | 2022-04-29 | 2022-05-17
Sample phase title block | ANALYSIS AND DESIGN
| User Interface |  | 2022-05-17 | 2022-05-31
| System Design |  | 2022-05-17 | 2022-05-31
| Database Design |  | 2022-05-17 | 2022-05-31
| Prototype Design |  | 2022-05-17 | 2022-05-31
APPLICATION IMPLEMENTATION (SCRUM)
| User Interface |  | 2022-05-20 | 2022-05-23
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | Class and Base functions |  | 2022-05-20 | 2022-05-23
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | Database Creation |  | 2022-05-20 | 2022-05-23
| Linking Classes, functions and database |  | 2022-05-20 | 2022-05-23
APPLICATION TESTING
| 1st round Unit Testing |  | 2022-05-20 | 2022-05-28
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | 1st round Integrated Tetsing |  | 2022-05-20 | 2022-05-28
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | 1st round System Testing |  | 2022-05-20 | 2022-05-28
| Linking Classes, functions and database |  | 2022-05-20 | 2022-05-28
| 2nd round Unit Testing |  | 2022-05-28 | 2022-05-31
| 2ndround Integrated Tetsing |  | 2022-05-28 | 2022-05-31
| 2nd round System Testing |  | 2022-05-28 | 2022-05-31
| Linking Classes, functions and database |  | 2022-05-28 | 2022-05-31
| 3rd round Unit Testing |  | 2022-06-01 | 2022-06-17
| 3rd round Integrated Tetsing |  | 2022-06-01 | 2022-06-17
| 3rd round System Testing |  | 2022-06-01 | 2022-06-17
| Linking Classes, functions and database |  | 2022-06-01 | 2022-06-17
| Final Unit Testing |  | 2022-06-18 | 2022-07-29
| Final Integrated Tetsing |  | 2022-06-18 | 2022-07-29
| Final System Testing |  | 2022-06-18 | 2022-07-29
| Linking Classes, functions and database |  | 2022-06-18 | 2022-07-29
DELIVERABLES/DOCUMENTATION
| Project Requirements |  | 2022-04-30 | 2022-04-30
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | System Requirement Specfication |  | 2022-05-18 | 2022-05-18
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | Technical Design Manual with functional prototype |  | 2022-06-01 | 2022-06-01
| System Prototype with basic functions, 1st Draft Project Progress Report |  | 2022-06-18 | 2022-06-18
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | Final Project Progress Report |  | 2022-06-25 | 2022-06-25
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | Functional Modules, Module and Integrated System Test Plan. |  | 2022-07-15 | 2022-07-15
| Progress Report with Final Document Draft, User Manual Draft, Test Summary, Integrated Module Functionalities |  | 2022-07-30 | 2022-07-30
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | Final Product and Documentation (User Manual, Technical Documentation, Project Video) |  | 2022-08-20 | 2022-08-20
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | Final Presentation Slides |  | 2022-08-20 | 2022-08-20