## Sheet1
Task | Start Date | End Date | Duration
SGTours | 2022-04-09 | 2022-08-27 | 140
Scheduling | 2022-04-10 | 2022-04-12 | 3
Resource Planning | 2022-04-10 | 2022-04-12 | 3
Project Website | 2022-04-13 | 2022-04-13 | 1
Gather requirements from stakeholders | 2022-04-13 | 2022-04-16 | 4
Research on existing applications | 2022-04-13 | 2022-04-17 | 5
Identifying functions from existing applications | 2022-04-13 | 2022-04-17 | 5
Software Development Methodologies | 2022-04-14 | 2022-04-17 | 4
Develop Use Cases | 2022-04-18 | 2022-04-29 | 12
Finalizing functional requirements | 2022-04-29 | 2022-05-17 | 19
Non-functional features | 2022-04-29 | 2022-05-17 | 19
Security Features | 2022-04-29 | 2022-05-17 | 19
User Interface | 2022-05-17 | 2022-05-31 | 15
System Design | 2022-05-17 | 2022-05-31 | 15
Database Design | 2022-05-17 | 2022-05-31 | 15
Prototype Design | 2022-05-17 | 2022-05-31 | 15
User Interface | 2022-05-20 | 2022-05-23 | 4
Class and Base functions | 2022-05-20 | 2022-05-23 | 4
Database Creation | 2022-05-20 | 2022-05-23 | 4
Linking Classes, functions and database | 2022-05-20 | 2022-05-23 | 4
1st round Unit Testing | 2022-05-20 | 2022-05-28 | 9
1st round Integrated Tetsing | 2022-05-20 | 2022-05-28 | 9
1st round System Testing | 2022-05-20 | 2022-05-28 | 9
Linking Classes, functions and database | 2022-05-20 | 2022-05-28 | 9
2nd round Unit Testing | 2022-05-28 | 2022-05-31 | 4
2ndround Integrated Tetsing | 2022-05-28 | 2022-05-31 | 4
2nd round System Testing | 2022-05-28 | 2022-05-31 | 4
Linking Classes, functions and database | 2022-05-28 | 2022-05-31 | 4
3rd round Unit Testing | 2022-06-01 | 2022-06-17 | 17
3rd round Integrated Tetsing | 2022-06-01 | 2022-06-17 | 17
3rd round System Testing | 2022-06-01 | 2022-06-17 | 17
Linking Classes, functions and database | 2022-06-01 | 2022-06-17 | 17
Final Unit Testing | 2022-06-18 | 2022-07-29 | 42
Final Integrated Tetsing | 2022-06-18 | 2022-07-29 | 42
Final System Testing | 2022-06-18 | 2022-07-29 | 42
Linking Classes, functions and database | 2022-06-18 | 2022-07-29 | 42
Project Requirements | 2022-04-30 | 2022-04-30 | 1
System Requirement Specfication | 2022-05-18 | 2022-05-18 | 1
Technical Design Manual with functional prototype | 2022-06-01 | 2022-06-01 | 1
System Prototype with basic functions, 1st Draft Project Progress Report | 2022-06-18 | 2022-06-18 | 1
Final Project Progress Report | 2022-06-25 | 2022-06-25 | 1
Functional Modules, Module and Integrated System Test Plan | 2022-07-15 | 2022-07-15 | 1
Progress Report with Final Document Draft, User Manual Draft, Test Summary, Integrated Module Functionalities | 2022-07-30 | 2022-07-30 | 1
Final Product and Documentation (User Manual, Technical Documentation, Project Video) | 2022-08-20 | 2022-08-20 | 1
Final Presentation Slides | 2022-08-20 | 2022-08-20 | 1
Final Submission | 2022-08-20 | 2022-08-20 | 1